## Followup
Topic | Issue | Description | Issue date | CRNSP owner | Owner | Due date | Status | Status date | comment customs | Status CRNSP 20/1/2021 | Meeting WG R&D 28/1/2021 | Status CRNSP 10/3/2021 | Meeting WG R&D 25/03/2021 | Status CRNSP 19/5/2021 | Status CRNSP 16/11/2021 | Status CRNSP 19/1/2022 |  | CRNSP 09/03/2022 | Status | Notes WG 18/5/2022 | Notes WG 2/6/2022 | Acrhive 2/6/22 | CRNSP 13/9/2022 | Preliminary response | CRNSP 10/11/2022
General | SLA/MoU | Proposed SLA/MoU will be discussed internally and the remarks will be shares asap | 2019-09-26 |  | Chris Declerck | not known | Markup MoU/SLA received and under review for reaction | 2020-05-13 | Markup MoU/SLA submitted to stakeholders and topic to be discussed in Steering Group | Any update? |  | update? | Bart E: no update yet, Pieter would contact Johan VD -> has this already taken place? This must be done first. Customs is waiting for input from Johan action : Pieter Haesaert | According to Johan Van Dingenen, there was no contact yet with Chris on this point. | Johan Van Dingenen is consolidating remarks. Steering committee requested MoU progress. Status? | CRNSP will work with Johan to draft a coherent MoU | Inhoud werd vastgelegd na overleg convenors WG Digitale Strategie. Een projectgroep zal de verdere uitwerking garanderen. Samenstelling van deze groep: - CRSNP (1 of 2 deelnemers) - Trade (1 of 2 vertegenwoordigers - AADA (tbd) - Naforna stuurgroep | Meeting Monday 11 april | Possible to receive questionnaire preparation? This is possible if we move the CRNSP meetings earlier, but even then the amount of questions cannot be dealt with -> better to provide an hour every two weeks for questions, especially once the test environments are available -> separate SUB WG? | proposition to schedule every 2 weeks a short meeting to interact between Swproviders and customs about specs and systems | Outcome of MoU 20/5 consultations: Johan VD will launch a proposal for a general collaboration at a higher level regarding implementations. The aim should be to manage the entire project set-up, including set-up and implementation at operators, of which ICT is only a part . Kristin - umbrella WG (DIGITALIZATION) would exist but not take place AAD&A/AGD&A indicates that this only takes place if topics are offered as agreed with Chris De Clerck. AAD&A/AGD&A -> who should notify the members of the VBO about changes -> the VBO itself, but not enough see also question about VGD / E-SAD in EMCS phase 4-> is not yet included in WG excise duties -> not yet known .. to the operators" |  | status? | Meeting between Johan Van Dingenen and Ivan Verborgh took place. | Status? Changes in co-operation with operators? | Mou will be put onhold due to focus on major projects
eGlobalisation | globalisation for entry under 51 procedure (IP) | no calculation of import duties | now | [21 empty] | new | Under investigation
eGlobalisation | technical issue | technical issue: apparently, for one correlation ID, 2 answers possible, eg reject answers with subsequent rejected, and other answer with accepted | [20 empty] | new | Will be investigated. | status? No new incidents identified by CRNSP | Investigation showed there was a problem between PLDA and FINDA. Configuration between both systems has been optimized. Ticket MSPPLDA-35319 has been put onhold until the end of the year.
MASP | planning | Is planning outlined feasible? | 2021-11-16 | [11 empty] | new | is it possible to share way of working, release or sprint planning so that the software providers can organize certain actions more aligned with the delivery by customs | Under discussion with our ICT-department of what can be shared. | status? | New provisional planning can be consulted on dedicated sheet (not yet confirmed by EU) PN/TS test is available, document is being prepared. However, not all interactions with other systems are ready yet. Planning will be indicated shortly | attention point for phased functionality in different systems | Postponement has not yet been officially communicated - the reason is that Europe has not yet confirmed this - no response to the proposal yet. Bart Engels - raise with Trade contact group - ? AAD&A/AGD&A -> they would have already raised this |  | status timing? | No change. | status, changes? | See tab Planning MASP
MASP | subwork group/workshop | Can a subworkgroup be established for evaluation of MIG's? | 2021-11-16 | [11 empty] | new | subworkgroup recommended to gather and answer questions when reviewing specs, discuss use cases etc | No extra subwerkgroup will be created. After publishing the mig a meeting will be organised to discuss the remarks on the MIG. | when? | Better to provide an hour every two weeks for questions, especially when the test environments are available -> separate SUB WG? Customs agrees internally on how best to go about this | status? | AAD&A/AGD&A wants to do this ad hoc. NCTS test system will be made available shortly as well as the documentation. Then a meeting will be organized. The purpose here was precisely to save time at customs to group the barrage of questions. 1 meeting every 2 months is not enough if delivery is due within 3 months. AAD&A/AGD&A will present this internally to Chris De Clerck |  | status? | Will be organised. For PN-TS a meeting will be scheduled. | confusion who has to deliver PN-TS. TS: postponed to 2 24For air: ground handlers? | Working groups for Air and Maritime will organised by the different communities. AADA will advise to invite also a representation of the softwareproviders.
MASP | documentation | Documentation, MIG's should be complete and finalized 8 months before go live date | 2021-11-16 | [11 empty] | new | additional documentation IDMS expected? | Which documentation? | MIG; what data elements and meaning | We are working hard on this. IDMS MIG by end of April (after Easter holidays, lead BA starts back in April). Question Peggy -> Possibility of providing sample XMLs. Question Johan Geerts -> Add date for publication of MIG. Question Michael GOMEZ - > overview messages and flow available? Remark Jeroen Van Nieuwkerk - > not all info is in PDF that are published - could this be published more conveniently - e.g. changes, more user-friendly MIGs | status? In particular for import, which was announced for end of April | MIG IDMS not yet available, XSD is reviewed internally at customs, after which a meeting will also be arranged. Term? The aim is to do this before the holidays, but is very uncertain |  | still now new version. Only 3 XML's in the documentation. MIG required! When can it be tested? | Still under analysis | status? Urgent! | See tab Delivrables projects
MASP | testing | test scenarios, examples? | [20 empty] | current XML examples are not sufficient; annotated examples with scenarios, with explanation within XML, with real business scenarios, cfr HMRC for CDS | Test messages will be made available. | status? | See tab Delivrables projects
MASP | instructions | Are there transition measures? Will the administrative instructions be kept up-to-date? What about amend, annull, regularisations of declarations? | 2021-11-16 | [11 empty] | new | status? | No regularisations, only amendments en invalidations. | status? | Will be added to the MIG. | status? | AAD&A/AGD&A - will be in the MIG, with indication when what can still be changed | NO | when MIG available? |  | status? | See tab Delivrables projects
MASP | technical questions not answered | no answers on technical questions/quid Q&A | [22 empty] | new | Clarification needed
AES | specs | national code tables? | 2022-03-09 | [14 empty] | recommendation is to avoid national codes, but are there specific national codes? The specs refer to national codes. | Legal department is making the preparations. To be included in MIG. | advise is to only use EU codes and only in exceptions (VAT, excise) national codes | AAD&A/AGD&A agrees - as little as National codes as possible should be the target | NO | Should be followed up, to avoid as much as possible national codes. Where to find the national codes? Should be avoided to have the national codes in the XSD in view of future maintenance | National codes are managed by legislative department. They will publish updated codelists. | status? CRNSP advises to limit national code lists as much as possible given the abundant EU code lists | Ongoing
IDMS | specs | key part of documentation missing | 2022-01-19 | Johan Geerts | [11 empty] | IDMS: XSD does not match documentation, business rules & validations missing, sequence diagrams missing | New XSD will be sent to day. Still 1 update needed: supplementary unit code has to be added. | tbd | Rework of MIG is ongoing. Customs will try to provide the Code Lists in XML | status? | see above - target is summer 2022 | NO | status? See above MASP |  | MIG still not yet full available? Sold version required | MIG will be published in the upcoming weeks.(before the end of the year) XSD IE415 has been published XSD other messages will be published in the upcoming weeks European Codelists have been published. First set of validationrules will also be published.
IDMS | specs | Location codes: will the current list be maintained? What with centralized clearance with which goods can be imported via other country. Can the location codes of that other country be used? If so, how? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | There is no consensus so far about how reference data like location codes will be validated. The current plan assumes that there will be a list of all relevant location codes that we will check. However, we don't know yet what that table will allow us to verify. If that table doesn't materialize, we will be unable to determine which location codes or location identifier types are valid for each member state. In that worst case scenario, we would not verify the location code for centralized clearance, accept the declaration, and if we subsequently get an error message from the office of presentation, forward that to the declarant. When the declarant sends in an amendment of the declaration, the message will be resent to the office of presentation.For Belgian location codes, you can find extra info on : https://financien.belgium.be/sites/default/files/Helpdesk_PLDA/MIG-Tech/AES/Location%20code%20identifiers%20AES.xlsx | new | No update | is our understanding correct that no location codes as currently in use will be used in PLDA? How will the presentation location be defined in IDMS? CRNSP advises use simple location codes (industry standards?) and make these location codes insightfull | AAD&A/AGD&A : some will be able to re-use but review is on-going. Aim to define 1 global code per physical location ICT is not involved in this - AAD&A/AGD&A will check internally Wouter : Currenty IDMS and AES will use the existing codes until the review has been completed Jim : location codes for this month not sent, = manual proecdure by Kristel -> was absent, AAD&A/AGD&A wil send |  | currently, for the same locations, different location codes exist; proposition is the postal code, as uniform and unambiguous as possible. Suggestion also for the working group operations. If location codes, then these should be downloadable for integration in software systems | Location codes are linked to a lot of internal entities. They can't be replaced by any other means of identification allowed by the EUCDM for the foreseeable future. A cleanup is currently being done. Publication of the full list is not possible due to the sensitive legal nature of certain codes. However, once we have a clean list, we will check with the concerned departments which parts we can make publically available. | status, further specifications available? According to type of location, also the customs office has to be delivered? Explanation needed.
IDMS | specs | Special procedures: there are many new data elements. Explanation needed how these have to be used. Does it impact on the existing reporting? Are the current lists of IPR maintained? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | No decision taken yet, but it was important to add these data-elements already to the XSD. | new | No update | status? | AAD&A/AGD&A : analysis is on-going | NO | status analysis? | Analysis is still ongoing | status? | Analysis ongoing
IMDS | test | what is the test environment? Is it identical as for H7? | 2022-03-09 | [14 empty] | new | Will be shared asap | status? | AAD&A/AGD&A : question asked internally, but no response yet |  | status? | TBD | status? | Will be different
IDMS | communication | what role to be requested for communication? | 2022-03-09 | [14 empty] | new | Will be shared asap | status? |  |  | status? | TBD | status? | Will be the same as for H7
AES/IMDS | specs | bij verwijderen van een item moeten in de wijziging/regularisatie (IE513) de lijnnummers terug sequentieel zijn of moet de verwijderde overgeslagen/”voorbehouden” worden/zijn? | 2022-03-09 | [14 empty] | new | Being analysed. Question has been submitted to DG TAXUD, as it is also important for communication with other Member States. | status? | AAD&A/AGD&A : received vague answer from Taxud , so needs to be clarified again by TAXUD |  | status? Current functionality of 'regularisation' as in PLDA will not be available, correct? At the other hadn, IE513 will be available, correct? | What is currently done via regularisations will indeed be done via IE413/IE513 messages. We prefer that this would include adding and removing items, but this has still not been confirmed by TAXUD. Otherwise this would require invalidating the old declaration and introducing a new one. The problem is limited to IDMS and NCTS. For AES, there is a possibility in the instructions that can be lawyered into meaning that adding and removing items is allowed. | any change or update? Will the line numbers be sequentional or unique? | No update
AES | specs | CL384 De controle-“Notification type” kan 1 van onderstaande waarden bevatten: 0 - Decision to Control (and requested documents if needed) 1 - Additional documents request 2 - Intention to Control Klopt het dat “1” overeenkomt met een documentaire controle en de overige 2 met een fysieke of wordt in geval van 2 nog een bijkomende boodschap gestuurd bij effectieve overgang naar controle met het type controle? | 2022-03-09 | [14 empty] | new | At the moment, type 2 is used at the moment the decision is made to proceed with a check, regardless of the type. If, during a documentary check, it appears that additional documents are required that were not requested in the first message, type 1 is used. Communication on physical control has not been established by Europe, and therefore not yet developed | for documentary controls, will it be foreseen that documents can be exchanged via the system? | AAD&A/AGD&A : will probably but be included in first operational version, but will in the long run be available, also in IDMS close | NO | to be clarified, is this answer for AES and for IDMS and NCTS 5 or separate? | This is a common approach for IDMS, AES and NCTS. The actual implementation date may be different for each system, but the implementation is not yet scheduled for any system at this point. | status update when to be implemented? | No update
IDMS |  | incoterm status 14 01 030 staat niet op EUCDM. Wat is dit? Wat moet er bij de leveringsvoorwaarden in “tekst”. | 2022-03-09 | [14 empty] | new | IE415 is based on the messages of CCI. In the messages of CCI these data elements are part of the messages. | question closed | archive | NO | answer not clear | The field 'text' can only be used for INCOTERM code 'XXX' (instructions from DDNXA). However, this is not listed in the legal documentation of codes that can be used in Belgium | clarification? | Code XXX is foreseen for IDMS and CCI. It is part of the codelist CL090.
AES |  | Volgens de presentatie van het MASP “Exit operations remain in PLDA” + “No more PDF’s”. Momenteel ontvangen wij geen XML-berichten hiervan maar krijgt de klant enkel een PDF wat gaat er concreet tijdens de overgangsfase dan gestuurd worden. Hoe lang zal die transitieperiode duren? | 2022-03-09 | [14 empty] | new | At the moment, the priority is on the declaration functionalities. The output process will then be converted to the new formats. No date has yet been set for this. | CRNSP recommendation to add a code to enable print of proof of export following the exit confirmation. Is this been discussed with the VAT administration | AAD&A/AGD&A : more clarification needed |  | Does the VAT administration accept the exit confirmed status as proof for export? Can this be discussed with the VAT administration? Otherwise VAT administration will continue requesting a print. | In the legislation a print out is no longer foreseen. | customs would check with VAT authorities whether the exit confirmed message is sufficient as proof of export instead of SAD. What is status? | Ongoing
AES/IMDS |  | opmaak referentie voorafgaand document oa voor N705, N703, N740. O.a. valt de bill of loading weg of wordt die hier geïncorporeerd? | 2022-03-09 | [14 empty] | new | Write off logic for goods flow will be added to the report. | status? | Bart Engels : C : should have been sent, otherwise pleas indicate | NO | answer not clear | Document will be extended with the new write off possibilities. | status? | Ongoing
IDMS |  | IDMS vs AES/NCTS5 XSD: in de xsd van de IE415 zit “alles” onder “ImportOperation” terwijl dit bij de Export (ExportOperation) en de Transit (TransitOperation) enkel hoofdgegevens bevat en overige op hetzelfde niveau zitten. Klopt dit? Daarnaast valt op dat “totalAmountInvoiced” bij export en import op een volledige verschillend niveau zit. | 2022-03-09 | [14 empty] | new | For IE415 the Administration used the European specs of CCI and for IE515 the specs of AES. | when is XSD available on website to check this? | see above - prio 1 for the B.A. | NO | answer not clear (in particular consignment level/goods shipment: 1 on 1 and then the items or not?; quid NCTS, different goodsshipment possible?) | All XSD's are available on the website and according to European instructions. (instructions for CCI were used for IDMS) | XSD can be incorrect? Can you recheck this topic? | New xsd has been published.
AES/IDMS/NCTS5 |  | PDF: Is er/komt in België of vanuit de EU een voorbeeld/gesuggereerde/verplichte lay out voor de documenten (oa 1 en 3) en/of de UGD? | 2022-03-09 | [14 empty] | new | Discussions about this have started at European level. Adminstration is following up on these discussions and if there is an agreement, they will use this implementation. | can you shed some light about the PDF requirements? Is it sufficient to have MRN reference on transport documents or other commercial document accompagnying the goods. | AAD&A/AGD&A : will check internally |  | status? | No decision taken yet | status? | No decision taken yet
IDMS |  | tabellen/tag: Waar is voor IDMS terug te vinden om welke code-tabel het gaat voor een bepaalde tag (de code, dit wordt normaal in de MIG in de voorlaatste kolom vermeld b.v. ”CL060”? Wanneer wordt de volledige Belgische MIG en denk ik vooral aan de rules en conditions voor IDMS verwacht? Zonder deze of enige uitleg omtrent nieuwe velden is het wel heel lastig om iets deftig voor te bereiden. Waar kunnen we de tabellen vinden als CSV/XLS/XML in verschillende talen die specifiek zijn voor de import op https://ec.europa.eu/taxation_customs/dds2/rd/rd_download_home.jsp?Lang=nl vind ik enkel deze voor de export o.a. CL791 additions/deductions zie ik daar b.v. niet tussen staan. | 2022-03-09 | [14 empty] | new | Will be added to the MIG. | status? | AAD&A/AGD&A : codelists will be in the MIG close | NO | when MIG available? | MIG will be published when we have a stable version. | status? | Codetables have been published on our website in JSON-format
IDMS |  | additions and deductions: Volgens de MIG is “splitCode” 14 04 097 en “adjustmenTypeCode” 14 04 095 onder D.E. 4/9 ik vind deze posten niet terug in EUCDM6.1. Zijn hier ergens lijsten voor beschikbaar? Zullen hier alle codes (CL791) op de 2 niveaus ingebracht kunnen worden of zijn er die enkel GoodsShipment of op GoodsShipmentItem zullen kunnen in België? | 2022-03-09 | [14 empty] | new | For the moment the Additions and deductions will be splitted based on the weight of the goods. We will publish a CL as soon the analysis has been finished | status? | AAD&A/AGD&A : codelists will be in the MIG close | NO | when MIG available? | MIG will be published when we have a stable version. | status? | Additions and deductions will be splitted based on the amount. The CL791 is published on the website.
AES/NCTS5 |  | nationale tabellen NCTS Phase 5 en AES. graag tonen op de website | 2022-03-09 | [14 empty] | new | Not available. Waiting for input of our legal department | status? | AAD&A/AGD&A :depending on "dienst wetgeving" - goal is as little nat.codes as possibles |  | status? | depending on "dienst wetgeving" - goal is as little nat.codes as possibles |  | See tab Delivrables projects
NCTS 5 |  | Wanneer business case met IE044 en verschillen - Ik vind het vreemd dat men wijzigingen kan opgeven met betrekking supporting documents en additional references - broken seals: moeten deze als missing worden opgegeven? - Unloaded not complete: Geeft men dan in eerste unloading report status van wat al gelost is? Zoja hoe aangeven wat gelost is en wat niet. Geeft men in volgend unloading report terug info eerste lossing en rest van lossing op? | 2022-03-09 | [14 empty] | new | The supporting documents and additional information that can be submitted via IE044 are additional information that can be attached as is already possible in the current NCTS. | attention, the question is about the unloading remarks following the NCTS arrival notificatio: should additional information be used in this case? Quid broken seals, and unloaded not complete | https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/masp-electronic-customs/toepassingen-masp |  | to be checked | In IE044 you should indicate the state of seals when seals where used State of seals data item fill in according to guideline: G0017: 'State of seals' = 1 in case that Seals are in good state (i.e. present and not damaged) 'State of seals' = 0 in case that Seals are not in good state (i.e. not present or damaged). Regarding unloading not complete: Dataitem unloading completion fill in according to guideline: G0186: <UNLOADING REMARK.Unloading completion> is used as a flag and it can contain 2 possible values: ‘0’ = ‘NO’ This means that the unloading of the goods is not yet completed; ‘1’ = ‘YES’ This means that the goods are completely unloaded. In the first IE044 only the data of the unloade goods In the final IE044 the data of all the unloaded goods also the ones who where in the previous IE044 | answer not complete, can you please recheck? | Ticket at EU has been created.
NCTS 5 |  | NCTS test omgeving beschikbaar? | [16 empty] | A document will be delivered with the necessary info-> how to connect, what can be tested, when, … | status? | AAD&A/AGD&A : short term -> test enviroment available, MIG + meeting to discuss preferrably before summer Session planned the 23th of Juin. |  | status? | Test environment will become available. | status? | Test environment is available Archive?
IDMS |  | geen codelijsten bschikbaar voor IDMS op EU site | [16 empty] | IDMS considered local by EU-> publication follows | status? | AAD&A/AGD&A : is correct, not available yet, when CCI goes in production some will be available. At that moment the lists will become available and customs will distribute. | YES | status? | In the future this will be published | status? | As already explained the EU is responsable for the publication of these code lists. We are not able to give an update about the availibility of these codelists
PN,TS | process | process flow, who needs to submit not clear | [20 empty] | new | Topic has been discussed during PN-TS Workgroup. Possible workflows where presented by customs. It is up to the economic operators to define who will send the data to customs : https://www.naforna.be/nl/system/files/20220627_Scenario_SWG_PNTS_Zee-Lucht_v2.xlsx | status? Apparently the excel is different to the information in the MIG. | Please specify which information in contradicting. As a general remark, it needs to be clear that the workflows from the Excel are only made available to show the interactions that would be needed for the scenario's which seemed most feasible to representatives from the trade community in the workshop. A lot of other scenario's can be imagined. Customs will not reject any scenario where other parties take up one of the roles defined in the workflow, as long as it is compliant with UCC article 139 §1 and §3.
NCTS 5 | code lists | what role of customs office is applicable for what message/dataset? | [20 empty] | new | cfr DDNTA | for certain message, the customs office to be declared for a certain role of the customs office. Can this be clarified? | Document will be added to the meeting report
NCTS 5 |  | loader remark, issue with transport documents; discrepancy between Word document and XSD. In particular for the transport documents group on consigment level and goodsitem level not consistent | [20 empty] | new | Could you tell us where exactly the discrepancy is located? In which XSD and on which location in what word document? | IE 044 XSD, compared to MIG is different. Eg Transport document. See email Johan | Futher clarification has been asked to DG Taxud.
TS | testing | how to indicate previous document for testing? How will this be organized for testing, in particular reference to ICS2 document? | [20 empty] | new | Before ICS2 R2 conformance testing is finished for EO and for BE customs, it will be impossible to test with real ENS MRN for PN-TS tests. Until then, random MRNs will have to be used. | random MRN: does that mean any MRN according to the UCC MRN rules per type of declaration | Compliance with UCC MRN rules per type of declaration is not checked, so any reference number can be used, as long as it fits the format defined in message specifications.
AES | previous document | previous documents: in NCTS this can be 0, is this also applicable for AES? (in IDMS there is always a previous document). Assumption is that 0 should mentioned. | [20 empty] | new | A previous document is not needed for AES. Given that for IDMS this is required to refer to a TSD or ENS document, I highly doubt that the reference can be 0. The XSD may allow it but the validation rules won't | can you clarify: if there is no previous document, what has to be mentioned? | If there is no previous document, there is no previous document. If there is a previous document, the reference can't be 0.
AES | testing | when is testing possible? | 2022-11-10 | [22 empty] | See tab Delivrables projects
MASP | URL's | overview of URL's per module needed to communicate | 2022-11-10 | [21 empty] | new | This overview is available in the EONGW MIG, and will be completed as more systems become available
TS | amendment | can an amendment be sent after receiving message linked/non linked (IETS030) | 2022-11-10 | [21 empty] | new | An amendment is possible after activation, but the amendment request is checked against the current version of the TSD, which includes some data elements originating from the PN: Date & time of presentation, customs office of presentation, location of goods, person presenting the goods and carrier. The validation rules for a combined TSD apply after activation, meaning that those data elements need to be included in the amendment request and in some cases need to corrrespond to the value of the current TSD version (so in case of activation to the value from the PN). The latter is the case for date & time of presentation, customs office of presentation and carrier.
TS | XSD + example | IETS928, IETS906 | 2022-11-10 | [21 empty] | new | XSD will be published in a new version of the MIG
PN | write off previous document | is it possible to make a flow diagram what has to be written off after what? | 2022-11-10 | [21 empty] | new | We are working on a diagram showing the write-off scenario's throughout the transition period towards the new declaration components. It will be made available as soon as possible.
EMCS 4.0 | testing | is it possible to test between two different legal entities? Eg from Ziegler to a client of Ziegler | 2022-11-10 | [21 empty] | new | In the SIM environment, there are 2 additional test licences, namely FRCA220001ZZZ and LUCC220001ZZZ. LUCC220001ZZZ will be able to be used as the destination; FRCA220001ZZZ will be able to use AADA as the "sender" to have an e-SAD sent from there with the tester as the destination.
EMCS 4.0 | testing | Updated Mig (V0.02) has been published --> corrective changes in IE801_national and IE815_national (language attribute for MaturationPeriodOrAgeOfProducts) | [23 empty] | New FAQ available

## Delivrables Projects
Project | XSD/YAML | MIG | European Codelists | National Codelists | Testmessages | Testenvironment | Remarks
PN- TS | Published | Published | Published | Expected | Available | Available
NCTS Ph5 | Published | Published | Published | Expected | Available | Available
AES | Published | Published | Published | Expected |  | Expected
IDMS ALL | Partially | Expected (20/12/2022) | Published | Expected |  | Expected | XSD IE415 has been published

## Planning MASP
Project | Voorziene Go Live | Comment
ICS 2 Release 2 | 2023-06-30 | Onder voorbehoud van aanvaarding EU
ICS 2 Release 3 | 2024-03-01
PN Air | 2023-06-30 | Onder voorbehoud van aanvaarding EU
TS Air | 2023-12-31 | Onder voorbehoud van aanvaarding EU
PN TS Maritime + Other transport modes | 2024-03-01
NCTS | 2023-06-30 | Onder voorbehoud van aanvaarding EU
AES | 2023-09-30 | Onder voorbehoud van aanvaarding EU
IDMS | 2023-10-01
CCI | 2023-12-01

## Archived
Topic | Issue | Description | Issue date | Owner | Due date | Status | Status date
PLDA | Clear-off failed = starteam nr 31086 / JIRA-1278 | As we understood the data in the reply message after a cancellation request message has changed. Therefor it is not possible to cancel a message for when a regularization (new) message was created. Is this problem a known issue ? can we have the starteam number ? |  |  |  | OK | 2019-11-20 | archive
PLDA | no cancellation message sent | PLDA returns mail to declarant with cancellation of accepted (MRN) message and no cancellation message is sent. Status? New returns: OK, but old ones still missing. Polling or not? |  | Bart Cieters |  | Original problem is already solved. | 2019-11-28 | solved
PLDA | Rounding problem of the calculated duties |  |  |  |  | OK, solved | 2019-11-28 | solved
BeGate | BeGate consolidation versus regular consolidation (globalisatie) | Chris Declerck will provide an update |  | Chris Declerck | not known | Chris will provide update. Published on website NF; 10 Jan 2020 | 2020-03-11 | solved
PLDA | REX | Singapore U177 code: code not known | 2020-03-11 | TBD |  | Solved | 2020-05-13 | solved
TARBEL | Missing information | In the Tarbel extract we get, the excises for tabac are missing. Samples given by Martin |  | Sonia Debois |  | Tarbel codes have never been integrated in Tarbel. Otherwise there is the risk that the excises will be paid twice. |  | solved
PLDA | Test database not up to date | PLDA tests : tarics are not updated since 01/07/2019, DPU incoterm missing, a lot of Unexpected errors. | 2020-01-01 |  |  | New topic This is correct. Version of Tarbel is not automatically updated. Bart has asked how the production dbse can be linked to the test environment. Unexpected errors: this occurred only 1 day. This topic seems to be solved? Can this be confirmed also by customs? | 2020-05-13 | Solved
EMCS | EMCS 3.4 big bang 13 February 2020 | MIGs ready now published on website. Test environment would have been ready but not communicated. What is test plan? Test scenarios, planning to be agreed. Communication to private sector and customs internally? Communication to WG Excises? | 2019-11-20 | Jurgen Van hooyland |  | Release is not yet available for testing. Example message, in particular the 'closure of a movement' message. Update? | 2020-05-13 | archive
PLDA |  | BE-GATE -> Vroeger kon dit afgeschreven worden met IM Y, en heb je 10 dagen tijd voor de aanzuivering. Dit blijkt niet meer te werken in PLDA. De douane gaf aan onze klant/customer service dat dit met IM A dient te gebeuren, maar hoe moet het dan de met verificatie. Moeten de goederen ter plaatse blijven? |  | Bart Cieters |  | New topic |  | Problem solved. Additional info 44-SIMP-BEGATE has to be added to the declaration.
PLDA | Locations codes box 30 | New format |  | Bart Cieters |  | Format OK. Issue of GDPR rules with possible solution of SFTP server: analysis in progress. No automatic update. NxPort to be checked with laurent. Latest update received. Archive as solved? | 2020-05-13 | archive
PLDA | Incoterm missing | DPU not accepted in test and production | 2020-01-01 |  |  | Will be discussed by BE and NL with EU Commission. Check with legislation whether this can adapted at national level. Seems to be solved -> archive as solved? | 2020-05-13 | Solved
PLDA | Expired certificates | When certificate is expired, you cannot retrieve declarations with get Get status message. Certificate is linked to correlation ID instead of Certificate holder Not testable. Get status message 'solution' is not a structural solution according to us. Eg cancellation message. What is strategy to improve the current situation on the longer term? |  | Bart Cieters |  | Must be monitored over a longer period to evaluate success of changes Some issues again | 2020-05-13 | Can be archived. Follow-up will be done with the problem of the missong exit confirmations
PLDA | Declaration type D - Starteam 31295 | If the type D declaration receives after arrival of the vessel the error that the B/L item has been written off already the declaration can no longer be cancelled nor regularized. It goes without saying that the system cannot be used as long as this bug exists. Is there a solution or workaround ? Extra ticket 31843 / JIRA-1739 has been created for this issue. The tickets are part of the scope of PLDA18.1. Has this ticket been delivered? If so we will test and make our customers aware of the possibilities. At what time is the debt taken into account ? MRN or Release ? Ticket is part of PLDA18.1 and will delivered for testing by mid July. Also Ticket 31856 ( Problem Martin Goblet) is part of this release. Tickets have been delivered in PLDA18.2. Have they been tested on ACC? What is status? |  | Bart Cieters |  | Change is implemented in production with release 18.1. Question is whether it can be tested. Customs can manually confirm arrival so that type D declaration can be tested. Issue date problem will be solved by release 18.4 next week Wednesday. JIM has given a sample where the problem with the foreigner still exists. Frank has send examples where the date is still not right. Release 19.1 of PLDA will issue mentioned by Jim solved, no validation on postcode. Issue with dates should be solved now. Issue date/acceptance date is now solved. 19.1 is foreseen in March. Issue of currency changes between issue date and acceptance in case of declaration between two months. Status? | 2020-05-13 | Solved
PLDA | Starteam number 23222/ JIRA-1108 | Customs will, together with IBM and ICT, investigate whether following statuses can be transmitted. - Financiële afhandeling opgestart ( contante betaling) - Klaar voor controle - Controle door MODA The statuses were added to the request. They will be taken into account when the PLDA will be reworked. At the latest it must be ready before end 2020. |  | Bart Cieters |  | No changes in current PLDA system. Will be part of future system for UCC changes. For later | 2020-05-13 | Archived (8/7/2020)
eGlobalisation | Communicatie | 15 oktober 2020 toelichtingssessie, open sessie. Vraag aan de douane dat ook de softwareproviders kunnen deelnemen. Oorpsronkelijk had CRNSP ook voorgesteld om toelichting te helpen geven trouwens. | 2020-09-16 |  |  |  |  | Archived
Brexit | availability of test environment for Brexit | When will test environment be available for Brexit tests? | 2020-07-02 |  | Bart Cieters |  | New topic | Archived | According to Bart, probably first the second test environment will be used for Brexit testing. Bart will communicate when what version will be available in what environment for Brexit testing. Expected after summer. Status?
Brexit | Brexitnota | vak 34a: land van oorsprong: ook wijziging van landencode? | 2020-09-16 |  |  |  | probably country code GB? | Archived
PLDA | Box 2 exporter information for import declaration | Box 2 Exporter mandatory for import. In the current legislation as of the 1st September this box is mandatory. This is a big change for the traders so this change will be postponed until the 1st of March 2020 Are the PLDA specifications be adapted, eg Enig Document? Not yet today! For which customs procedures and validation rules? Communication plan to private sector? Communication internally customs? + Additional question: In case the goods are being placed under IPR in member state nr 1 (procedure 5100) and are being sold to and processed by a buyer in member state nr 2 (in this case in Belgium) (procedure 5154), which consignor needs to be mentioned for the buyer in member state 2? His supplier or the consignor, who sold the goods (to member state 1) before they entered the Union. | 2019-11-28 |  | Bart Cieters | 2019-03-01 | Adapted XSD scheme will be provided by mid December 2019. Currently only on header level, but should be made available on item level. Until 28/2 the exporter may be included in the message and as of 1/3 it will be obligatory. For declarations with procedure code 4071 this data element will be required. For Globalisation, this was currently not yet foreseen. Must be checked. No update, XSD missing, and consignor must be added at item level update? Postponed to May 1, still questions about requirements; Is box 2 information for a 4071 declaration required, could result in much large item lines and is this actually realistic? Is it also obliged with globalisation? | 2020-05-13 | According legislation it is mandatory for toelichting H. Will also be mandatory for globalisation. | to be archived
PLDA | IPR issue for quarterly globalisation | EIDR authorisation is required for PLDA but is legally not required and regional directorate refuses to deliver EIDR authorisations in certain cases. C4T would receive a dummy authorisation code to test | Q1 2018 |  | Bart Cieters |  | no dummy autorisation received until now; WIP, Bart will appoint colleague to take this up. Sonja Dubois checkt authorisations. Status? | 2020-09-16 | Solution via ticket MSPPLDA-2519. Part of PLDA20.1 expected end of August Not yet implemented, according to Helpdesk in October | to be archived!
BREXIT | follow up changes | Brexit : any changes forseen ? | 2020-01-01 |  |  |  | update? | 2020-05-13 | Updates for Import, Export and Transit Countrycode Nothern Ireland : XI Countrycode Great Britain excluding NI : XU | to be archived
eGlobalisation | Documentation | The MIG will be made available asap | 2017-11-23 |  | Bart Cieters | not known | MIG received and reviewed by CRSNP. Remarks and comments will be sent 11 March Answer received May 11, reviewed by CRNSP | 2020-07-02 | MIG adapted and sent by Bart to eGlobalisation participants 2/7/2020 | to be archived
NCTS | NCTS without reply | Potentially linked to missing validation errors If special character in name of person, then no answer If two times previous document, should receive a validation error instead of no answer If description is too long, no answer If wrong office of transit, exit, no answer | 2019-11-20 | Ziegler | Lindsey Jacobs Sjoerd |  | If no tickets, Martin will be contacted for examples. Sample for special char given, no update. Exit office works special characters: solution is identified. New version will be testable, in NCTS 10.3 in February in production Status? | 2020-09-16 | Was part 10.3 but has been removed due to problems in PROD. Is now part of NCTS10.5 Update? Issue with special characters is still existing, eg "é" in capital letters | to be archived
TARBEL | Errors given in PLDA declarations | Tarbel asks additional calculation codes FA/FB/FF, but they do not appear ont the Tarbel and not in the extract. Samples given by Martin, see mail from christian.viaene on 29/08/2019 | 2017-12-15 | Ziegler | Sonia |  | New topic, old request this is info from PLDA. Codes available on website additional calculation codes. Should be mentioned in declaration validation rules. Bart will provide the info (forfaitaire waardes) Status? | 2020-05-13 | ITEM_0176, ITEM_0177. These codes are linked to measure 490 in Tarbel. | to be archived
PLDA | national codes | For different documents, authorisations there exist a double national code, besides the UCC codes. Proposal to remove national codes if UCC code exists | 2020-03-11 |  | TBD |  | Update? | 2020-05-13 | Normally the national codes are more specific than the European codes | to be archived
BeGate | Specs not clear | Brucargo and Luik not with identical specs. According to GlobalSign, certificate as mentioned in MIG is not possible | 2020-05-13 |  | TBD |  | New topic | 2020-05-13 | According Crossroads it is identical. Archive? | to be archived
eGlobalisation | Specs not clear | when update of MIG? Some fields should not be included. | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation | Specs not clear | Response messages. According to Bart, the response messages should be equal to SAD Response. Need for more detail, in particular for list of error messages. The SAD Response cannot be equal to the response message for eGlobalisation (eg sequence nr). | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | List of validation errors: when will it be published? | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | Deferral payment not accepted as payment method. Always type A to be mentioned as payment method: or is only to be mentioned for the end message? | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | Seals is niet required. Is optioneel, maar mag in het initbericht niet vermeld worden.: volgens ons moet dit verwijderd worden. Lijkt niet van toepassing voor globalisatie | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | Code 53 is not allowed: is this code in any case allowed? Only for Init message or also for sequential messages? | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | SADGlobImportInit cannot be annulled. Question: can this message be adapted or corrected? | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | Timing: to be discussed in subworking group eGlobalisation | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation |  | Testing: proposal from CRNSP: shadow messages for real clients by software providers. This could give trust to all stakeholders (customs control departments, customs ICT, autorisation holders and software providers. | 2020-05-13 |  | Bart Cieters |  | New topic | 2020-05-13 |  | to be archived
eGlobalisation | Testomgeving | Testomgeving beschikbaar, maar alle wijzigingen voor eGlobalisatie zitten in 20.1 terwijl de testomgeving 20.0 is. Wanneer zou 20.1 gepland staan: eind september. Doel is dat begin oktober de pilots zouden testen. Afhankelijk of testomgeving zou lukken of niet. Vraag aan Bart Cieters: wanneer zal testomgeving 20.1 versie beschikbaar zijn? | 2020-09-16 |  |  |  | new topic |  |  | to be archived
eGlobalisation | Timing test, go live | Termijn: tijdens de subwerkgroep eGlobalisatie vergadering is gemeld dat eGlobalisatie verplicht wordt uiterlijk tegen einde Q4 2021 ? Wat is de beslissing van de douane? | 2020-09-16 |  |  |  | New topic |  |  | to be archived
eGlobalisation |  | volgende meeting na opstart van de pilots, is er een verslag van de meeting? | 2020-09-16 |  |  |  | New topic |  |  | to be archived
PLDA |  | INF portal not available for Belgium |  |  | Bart Cieters |  | New topic | 2020-07-02 | INF portal would become available beginning of August. There will be a newsflash on the National Forum website. According to customs there is no impact for PLDA. | to be archived
PLDA | exit confirmation | Issue raised in relation to lost exit confirmation messages in PLDA. It relates to export declarations in period Feb-beginning March 2018. Although exit confirmation was received, export declarations have been annulled by customs. | 2020-07-02 |  | Bart Cieters |  | New topic | 2020-07-02 | There must be a trace of the exit confirmations. MRN's to be sent to Bart. Bart will ask to investigate the issue. | to be archived
NCTS 5 | Specs not clear | NCTS 5 999 house consignments met 9999 items? Onderliggende details van zending meegeven. Probleem mogelijk bij ontvangende NCTS. Nu: 1 consignment in bericht maar als er meerdere consignments zijn? Serieuze aanpassing. Wat betekent het consignment/house consignment/consignment items niveau? | 2020-09-16 | Ziegler |  |  | New topic | 2020-09-16 | request to have an update session about the specs | to be archived
PLDA | Type D | type D: nog altijd fouten. Voorbeelden doorgestuurd door Martin aan Bart. Schip komt binnen, ipv release krijg je foutmelding. Terug insturen en dan direct release, dus de gegevens op de aangifte waren correct | 2020-09-16 | Ziegler | [5 empty] | to be archived
TARBEL | Errors given in PLDA declarations | Oude TARBEL: fouten bij BTW berekeningen, gemeld aan Helpdesk | 2020-09-16 | Ziegler | [5 empty] | to be archived
PLDA | Rex nr | Rex nr is 27 characters for the Philipinnes. In Web application it is possible but not in the XML. Too many characters error | 2020-09-16 | Organi | [5 empty] | to be archived
Brexit |  | Code vervoerwijze grens: Calais/Eurotunnel: code 2 rail volgens de FR douane. Ferry met RoRo: 1. BE akkoord voor uitvoeraangiften in BE? | [7 empty] | to be archived
Brexit | RoRo | Container op chassis: hoe ziet de BE dit en andere Lidstaten: RoRo of container? | 2020-09-16 | [6 empty] | to be archived
EMCS | testen | Er zou een email gestuurd zijn naar CRNSP met de vraag om te testen. Maar niet iedereen heeft die gekregen. Recipients Id niet meer correct. Update was niet duidelijk gecommuniceerd. Hoe kan communicatie beter? | 2020-09-16 | Deloitte/Organi/Dorothy | [5 empty] | to be archived
PLDA | Testsystem | Brexit not yet available? NO communication? | 2020-11-18 |  |  |  | New topic |  |  | to be archived
PLDA | Testsystem | TARIC version from June | 2020-11-18 |  |  |  | New topic |  |  | to be archived
EMCS | Testsystem | Brexit adapted? | 2020-11-18 |  |  |  | New topic |  |  | to be archived
NCTS | Testsystem | Brexit adapted? | 2020-11-18 |  |  |  | New topic |  |  | to be archived
eGlobalisation |  | Status update | 2020-11-18 |  |  |  | Basic tests seem to be OK | 2020-11-18 |  | idem
Brexit | RX Seaport | For Zeebrugge Ferry transports it seems that messages only will get a green light if sent directly to RX Seaport instead of eBalie. Question to be asked to RX Seaport | 2020-11-18 |  |  |  | New topic |  |  | to be archived
General | requests from other National Forum WG | Are there any requests from other WG that need to be discussed in WG ICT/R&D? | 2019-11-20 |  | Bart Cieters & Pieter Haesaert |  | Consolidatie: schema maken, is het voorstel; RTO overbrengingsnota: idee was bericht op te maken. MIG is opgemaakt zelf, bericht is gemaakt. Is klaar om gepubliceerd te worden. Specs zijn klaar. Kissik: eerste faze in ontwikkeling. By mid this year first authorisation EORI. update? | 2020-05-13 | Implementation transfer temporary storage will be part of PLDA20.1 | Status? Pilot projects when? | Archive
PLDA | Cuscar - TS transfer in Belgium | No changes have been planned for the CUSCAR messages. Probably the EIR-message will be used for the movement between temporary storage locations. Are there any changes foreseen to the EIR-message ? |  |  | Bart Cieters |  | A message is developed. An adapted XSD will be made avalaible by mid December. Will be in production Q2 2020. WG Binnenbrengen will be informed. Status? | 2020-07-02 | Implementation transfer temporary storage will be part of PLDA20.1 MIG and XSD schemes published. Additional remarks: minicuscar will not be abolished, will continue to be applicable until new 'goederencomptabiliteit' system under MASP (scheduled in 2024) | status transfer declaration with EIR message? | Archive
PLDA | Errors PLDA | New statistics? First remove bug with type D declarations to see improvements. |  |  | Bart Cieters |  | New statistics will be added to report. Compared with Jan/Feb to previous quarter: decrease of 17% less errors. Error 'goods not arrived' 37% down. Update? | 2020-07-02 | See new tab. Significant reduction of errors 'goods not arrived', probably due to increased usage of declaration type D |  | Archive
GCB | GCB issue | There is already a long issue with partial arrivals in the GCB administration. If the shipment arrives with 3 separate flights, the first one seems no further written off and the customs systems seems to loose the data. This issue Is under investigation. Ticket 31856 has been created. Please report state of play. Will be part of PLDA18.2 or PLDA18.3 Not part of PLDA19.1 Status? |  |  |  |  | Scheduled for release 19.1. Frank wil provide example message. SSW has send a sample, no update Update? | 2020-05-13 | I have received an update and I'll contact SSW with further info. | status? | Archive
NCTS | Unloading message only after 24hr in Hasselt | NCTS normal procedure IE43 unloading permission is not sent by customs, only standard after 24 hrs. Message IE025 is waiting 1 day, this means, the operator is not allowed to unload the truck and submit the subsequent customs declaration until IE25 is received. Normale procedure "https://financien.belgium.be/sites/default/files/Helpdesk_PLDA/NCTS-Fiscus/notes_nl_sectie_iii_procedure.pdf" "Nadat het douanevervoer is toegekomen ter bestemming, wordt het kantoor van bestemming door de economische operator ter bestemming hiervan verwittigd met de kennisgeving van aankomst E_ARR_NOT (IE07). Indien het kantoor van bestemming de aankomst van het douanevervoer aanvaardt, wordt het kantoor van vertrek door het kantoor van bestemming hiervan op de hoogte gebracht met een C_ARR_ADV (IE06). Na de controlefase ter bestemming, waarbinnen een controle van de goederen kan plaatsvinden, geeft het kantoor van bestemming de goederen vrij van transit en verwittigt de economische operator ter bestemming hiervan met een E_GDS_REL (IE25). Terzelfder tijd worden de controleresultaten ter bestemming door het kantoor van bestemming verzonden naar het kantoor van vertrek met de C_DES_CON (IE18). " |  |  |  |  | must be transferred to the WG Special Procedures to be checked with Bart Engels: status update? | 2020-05-13 |  | status? | Archive
eGlobalisation | testen | Status pilots, feedback to the operators? What is status from PLDA point of view? | 2021-01-20 |  |  |  | New |  |  | New | Second infosession will be organised. | archived
eGlobalisation | testen | When update of eGlobalisation system, when new improved release? | 2021-01-20 |  |  |  | New |  |  | New | ????
eGlobalisation | testen | Is it possible to provide example messages for each of the messages? | 2021-01-28 |  |  |  | New |  |  | New
PLDA | Testsystem | Is it correct that ICT decided not to update the Test environment? | 2021-01-20 |  |  |  | New |  |  | New | No
H7 | MIG | when new, corrected MIG? A lot of inconsistencies. Sequence diagram? All messages? | 2021-01-20 |  |  |  | New |  |  | New | Other meeting
H7 | Testsystem | when testsystem available? | 2021-01-20 |  |  |  | New |  |  | New | Other meeting
PLDA | Amend declarations | Because of new way of working, declarations that have been verified and on which anomalies have been established are left in the BTB applications in a status MRN and cannot be processed any further. In the PLDA web they are left in status “onregelmatigheden vastgesteld” Customs does not send any further messages. In practice this means that no proof or document is received from customs by the importer or exporter in order to prove the regularly imported or exported goods. On the other hand we understand that some customs offices demand a new electronic declaration without reference to the previous one, leaving the system with two declarations for the same shipment. The issue is also escalated to the WG “Algemene Bepalingen”, but it is necessary that PLDA provides a uniform and automated solution (as in NL,DE..) An exhaustive e-mail has been sent to WG Algemene Bepalingen in order to supply a solution. It’s correct that PLDA has to provide a uniform and automated solution, but we are also waiting for a clear guideline of our experts. As long as we don’t receive this guideline, PLDA will not be changed. An internal meeting will be organized to discuss which changes to PLDA have to be done. What is status? |  |  | Bart Cieters | IDMS | WIP Status? | 2020-05-13 | No update | status? | Archive
NCTS |  | NCTS BE009A : referentie missing in response : Sample will be given by ABM data | 2020-01-01 |  |  |  | New topic problem exist already since a long time, is under investigation (Frank) Problem is still existing, Status? | 2020-05-13 | Will be part of NCTS10.6 | status? | Archive
TARBEL | Errors given in PLDA declarations | Tarbel asks additionnal codes 2500 or 2501 even if a preference is choosen. Samples given by Martin, see mail from christian.viaene on 29/08/2019 | 2016-03-31 | Ziegler | Sonia | IDMS | New topic, old request Problem is still existing, status? | 2020-05-13 |  | status? | Archive
TARBEL | Errors given in PLDA declarations | Tarbel asks U088 (Agreement with CA) for other countries that are not involved (like CH). Samples given by Martin, see mail from christian.viaene on 29/08/2019 | 2018-02-14 | Ziegler | Sonia | IDMS | New topic, old request Status? | 2020-05-13 |  | status? | Archive
PLDA | automatic annulment | in case of NCTS clear off issue/write off issues, the subsequent declaration in PLDA should come into automatic annulment, but message not received, only customs error message received. The annulment of the declarations is however confirmed by email. | 2020-03-11 |  | TBD |  | Update? | 2020-09-16 | Ticket MSPPLDA-2480 has be created to allow to use the LRN with another message. Ticket is part of PLDA20,2,0 Status? | status? | Archive
eGlobalisation | testen | Error message without sequence nr in subsequent message; only LRN is mentioned | 2021-01-20 |  |  |  | New |  |  | New | Archive
EMCS | data | Missing data element alcoholic strength. Is there a mapping issue in BE EMCS? IE801 received but without these data elements to be printed. Ticket Jira 858. | 2021-01-20 |  |  |  | New |  |  | New | Archive
General | Communication and authentication | IT customs wants to move NCTS and PLDA to the same communication protocol Following protocols are offered: Web services/FTP/AS2/IDcard or token. A separate meeting will be organized by the CRSNP communication providers for the members that perform communication. Descartes will take the initiative and inform the result to customs. A meeting with a smaller group of software providers has been scheduled. First meeting will take place on 23 November 2017. The members have expressed their concern in a message to the customs authorities regarding the new way of communication. The topic has a general impact on all economic operators and should be treated on a national forum level. A preliminary meeting with a small delegation of communication providers is foreseen on 6/2 10.00 h in NG probably room A13 Meeting is foreseen on 8/2/2017. Meeting Room A08 The report on the meeting “communicatie en authenticatie” held on 8/2 sheds more light on the resolution of this issue. We are looking forward to the next meeting on 19/4. No further steps were taken. The issue is temporary suspended for more urgent matters. As soon as the IT provider will reactivate the project you will be informed. Is there any further evolution ? What is status? "By the end of October 2019 the AIX Servers used by NCTS and Tarbel have to be sourced out. This is the priority number 1. Once this has been done new meetings will be organized." As we understood from the brainstorming meeting of 24/10 new meetings of this WG should be planned ? When is the next meeting ? Has nothing to do with high level vision document, to our opinion. | 2017-11-23 |  | Bart Cieters |  | Assumption is no impact for software providers; For NCTS, a component will be replaced. In future, it will be replaced. No update Sjoerd: NCTS phase 5 harmonization, including PLDA will trigger changes Bart is scheduling meeting end of May with representatives Björn Bollingh, Janik Monsieurs, Ronny Aerts | 2020-07-02 | Prepatory internal meeting has been scheduled on 13/7/2020. After this internal meeting a meeting with the 3 representatives of CRSNP will be scheduled. The new communication method will be applicable gradually for all MASP project items, beginning with the H7 dataset Meeting ging door op 1 september. Betreft communicatie voor alle instanties, met zelf authenticatie. Alle afzenders moeten gekend zijn. vertegenwoordiging via tussenpartij zoals Xcomm of Descartes wordt in overweging genomen. Tijdsvenster: 2023. Koen zal een samenvatting doorsturen. Systeem werkt per aangever: ofwel de effectieve aangever juridisch gezien ofwel het systeem dat aangiften instuurt voor meerdere aangevers. Eind oktober test met BPost. Reden van verandering: modernere architectuur. Standpunt CRNSP: tussenpartijen moeten ook. Communicatie niet enkel naar de bedrijven, maar vooral naar de softwareproviders. naast de operatoren moet CRNSP ingelicht worden. | As all new declaration functionality would run through new system, what about H7 data set? Will H7 dataset run in PLDA? Idem for NCTS 5? | All new declaration functionality. Not for eGlobalisation: this will be identical as for PLDA WG has requested a specific infosession about this topic for all interested parties. Bart will look internally to organise this. | Request to schedule an infosession about the new communication specs. Info during H7 infosession was not sufficient. | Bart Cieters will check ,there are many uncertainties, especially about the identification section | Specific meeting still needed in view of PLDA and H7. | archive
General | Planning | Overview planning customs projects. |  |  | Chris Declerck | 2019-12-30 | before end of year planning will be made available for the projects for which a date is known. release planning remains in WG R&D Overview of planning was discussed during WG ICT; timing and milestones of each component need to be clarified; tbd what need to be discussed in WG ICT feedback CRNSP: is there an update of planning? Main first concern is the accumulation of changes in 1 year of the planning as presented during the WG ICT: is this realistic? | 2020-07-02 | H7 has been postponed with 6 months. Yearly planning is in progress. For new projects, separate specific working groups can be started. New projects, new systems would not be discussed anymore in this working group. Question is who will co-ordinate between all stakeholders? | Any updates? What about 2022 roll out? | No update. | update? | changes are coming (NCTS + AES - planned for April - will be later) term is unknown (ASAP) | MASP planning: according to initial plan, the import data set is scheduled for Q4 2021. When is the MIG available? Subwerkgroep? | opmerkingen Johan ivm documentatie beschikbaarheid
General | Technical documentation | Following latest technical documentation was requested during the meeting before summer (XSD’s, MIG’s and Excel sheets): PLDA NCTS EMCS GCB AC4 GCA (transshipment) ECS (Charge report, codeco, transfert bericht, export manifest) ICS (ENS) EIR Be-Gate Globalisatie Tarbel 2 “Brexit” Excel sheets : validatieregels errors betaalwijze |  |  | Bart Cieters | 2019-12-30 | WIP. Adapted scheme for box 2 exporter, validation rules of SAD declaration. Specs with recent date (after mid Jan 2020) should be valid. Proposal for new web page with RSS feed functionality. Status? | 2020-05-13 | WIP | XSD scheme incomplete, test system for H7? | H7 will be clarified during H7-meeting | 15 april testing too short can we obtain a decision scheme what system needs to be used in what circumstances (H7, H1, Begate)? | "For the time being this date is being used. Period remains short. The final version was only published on 15/3. Existing functions are now compared with Annex B. Postponement is not allowed from the EU. Decision scheme is still provided by BC - there is a version in FAQ of H7 - see link https://www.naforna.be/fr/system/files/20210304_FAQ_H7_FR_v1.pdf shipments that come in error must be removed from the 'mailbag' and then treated separately -> yes Gerrit: Clarity about VAT rates? these are all included in tarbel at the level of 6 digits -> no possibility to have 2 rates if not included in tarbel. date of publication is requested by BC Specs about release of document -> not foreseen - what evidence can a logistics player impose on his customer - will be checked with service legislation -> action BC / Gerrit " | Can we have a status update regarding the publication of specs? Eg: eGlobalisation update. New XSD sent only to one company. On website still the old version, 2 versions.... Make clear that archive version is not to be used anymore. | archive
PLDA | Change “Charge report” to use as “Arrival at Exit” (IE507) | Next step is the transfer message between the forwarder and the handling agent. We understood from Customs that still one communication had to be set up between customs and the handling agent. Please provide state of play. When will this be ready for implementation ? No planning available yet. There are 4 handling agencies. In order to start the implementation we need to know their EORI number and communication provider. From 3 agencies we have already the info. A reminder has been sent to the 4th agency. As for Brucloud (Air) we understand that it is a limited success since users with al limited number of declarations do not want to pay for the service. In the latter case it has no added value. (taken from the report on the last meeting of the national forum). Please inform state of play or planning The solution for the transfer message can only be implemented after ticket 27924. With this ticket the use of the certificates will reviewed in PLDA. Status? What is link with point 6 cuscar/TS transfer in Belgium? |  |  | Bart Cieters | 2020-01-31 | Scheduled in PLDA 18.6 for January 2020 Status? Charge report can be sent. But still not clear when the 'goederenbehandelaars' will receive the messages. Can the flow be documented? When will it become obligatory? | 2020-05-13 | Url's to sent the info have been requested to the goederenbehandelaars. We haven't received all url's yet. | status transfer message for this topic? |  | When does it start? | Transfer message starts on 1/4 - for freight handlers. Declaration must be submitted by charge report declarants. And this as soon as the transfer to the handling agent starts. Note Martin -> this is only possible after the entire shipment has been received, and only then can the charge report be submitted -> there are partial shipments and the operation is not planned for this. The submitter remains responsible for partial shipments that are no longer in their possession -> will be examined internally by Klara Pasgang the goal is to get an answer about this this week | to be checked after 1 July | archive
PLDA | Declaration Type X | The declaration cannot be sent. Always the same error. D_NO_SIMPLIFIED_DECLARATION_FOUND Geen enkele vereenvoudigde aangifte werd gevonden. In the declaration case 40 refers to the MRN of the type B declaration. Request to the customs helpdesk learns that up to today no release to a declaration type X was ever received in Belgium. Will this type of declaration will be supported in future ? The simplified declaration is available in PLDA. To link both declarations to each other the same LRN has to be used.Our Legal department will send me in the upcoming days the legal base of all the data elements that can be changed. As we understand the weight can be changed, but since the weight in a declaration for bulk cargo has its influence on the value also the value must be modified in relation to the weight. Can this be adapted ? Further discussion with our legal department is necessary. Planning : after Brexit. Is there any planning ? No planning yet. The meeting with our Legal department still has to be organized. |  |  | Bart Cieters | IDMS | WIP. Status? | 2020-05-13 | No update. | Brexit done, what is status? |  | When does it start? | the adjustment that the value can be changed also within IDMS -> update in status. Mainly The bulk sector has a problem with this. | When in IDMS? Q4 2021? Go live 1 Jan 2022? | new system
PLDA | Missing exit confirmations | Examples available | 2019-11-20 |  | Bart Cieters | not known | Must be monitored over a longer period to evaluate success of changes Frank has sent a list of export declarations in October. There were 2 specific days with a communication problem. For the new ones, it should also be returned There are still cases that no exit confirmation are received, although the declaration is in status exit confirmed on the website. These cases seem to occur often with customs office of exit Zaventem/Brucargo. | 2020-07-02 | New examples have been investigated.At the moment of the confirmation of exit there was a problem with the signing of the messages. I have verified all the sent messages of May 2020 and I didn't find the error anymore. I can only assume that the problem has been solved. Problemen vorige week, voorbeelden doorgestuurd ivm bevestiging van uitgang. Als het niet via BruCloud gaat, dan zijn er blijkbaar problemen. | some new missing exit confirmations since Brexit 1 Jan 2021: examples available for exports via Zeebrugge via RX Seaport. No answer from PLDA helpdesk on this issue. In FR, exit confirmation OK, except of Eurotunnel |  | status? | according to BC did not occur again, was an issue in France with code lists for Calais (Ferry?). Dorothy has forwarded the list to helpdesk, cause could be missing information. If everything has been submitted correctly, the process should run smoothly. Is an organizational problem across the entire sector -> in Antwerp, statistics are compiled to detect the operators who often have to deal with this. Customs (ECS helpdesk) already has an overview of this. | Status? | new system: quid annulment of exit confirmation, legally allowed 90 days, system requirement seems to be maximal 1 month (contradiction)
eGlobalisation | Timing test, go live | CRNSP proposes following approach: - Once MIG and tested example messages received, then 2 months to analyze documentation with feedback in next R&D meeting; - If MIG documentation is acceptable, then agree acceptance criteria, test scenario and planning; Eg test period: 3 months and evaluate after each test milestone. Possible with pilots. In total this may be 6 months. - Once test OK, agree date for production and transition period, at least 6 months after succesfull tests; - Agree change management and communication plan for all stakeholders within customs and trade - Production go live: 6 months after succesfull tests with transition period of 6 months | 2019-11-20 |  | Bart Cieters | not known | All economic operators with autorisation for periodic supplementary declaration will be informed and will be asked when it is feasible to switch to new system. Bart will inform the WG when the communication will take place. Not yet decided who will communicate. Bart can agree with the proposed timing approach. update on planning during subworkgroup globalisation 17th March Letters sent to economic operators? Update? | 2020-07-02 | Customs decided to first send letters to the globalisation autorisation holders to request their readiness for eGlobalisation. Based upon the feedback from the autorisation holders, customs will decide upon the timeline. | status of letter to economic operators? |  | On 25 September, we have received version 1.3 available? On the website it is version 1.2. It is advisable to put the latest version on the website | Today or tomorrow 1.3 will be published, difference is consignor included in it. Production is active. To be archived | Monday 17 May live (SSW). | archive
TARBEL | performance, bugs | New tarbel is very slow Some bugs, potential adverse affects financially for customs. Bugs have been notified to customs. Extraction split in several XML's: status? | 2019-11-20 | Ziegler | Bart Cieters | not known | For extractions, bugs and extraction split, there were budget issues, will be resolved with change requests next year. Full extract crashes every month, last day of month extract always missing Budget was needed. Budget is available. But, first priority of Eurodynamics will be ecommerce. No timing is known. Status? | 2020-05-13 | European Dynamics is working on E-commerce. | status? Answers received from Bart & Sonja is that TARBEL is following after e-Commerce and Brexit. Consequence is that integration with TARBEL is not used or cannot be used | ED has delivered a solution. Installation is ongoing. | status? | Performance is better. Large files have been generated, but turnaround time is long (7h = 1 x per month) -> this afternoon a meeting with ED. Changes would go to production. The daily changes will also be included here -> together in 1 package | Status? | performance: no information whether acceptable
NCTS | message IE045 | In many cases, IE045 (exit conf voor transit) message is not received | 2020-05-13 |  | TBD |  | New topic | 2020-07-02 | Helpdesk has been contacted and no recent examples are available. However, it appears that there were issues in relation with status. | status? is still an issue |  |  | BC: will inquire at the helpdesk how often this still occurs - depending on the action or not | Status? | Latest months less issues apparently. Propose to archive
Emergency procedures | VIL project | feedback workshop: mid February meeting with Erik Verlinden, proposal for 10 or 11 Feb afternoon | 2020-11-18 |  |  |  | New topic |  |  | meeting to be scheduled |  | meeting with Eric Verlinden and CRNSP 10/2/2021 | BC: Not involved in this project CRSNP: usefulness of initiative is questioned for PLDA. VIL would now propose this to customs -> re-record on next WG BE: final documentation would already have been communicated to private sector. Project is completed -> financing is now being considered | Status update? | archive
NCTS 5 | specs | is it possible to organize an infosession? | 2021-01-20 |  |  |  | New |  |  | New | Will be organised | update? | BC: what needs to be explained -> large flow + planning (test /…)? Action: CRNSP will list expectations customs plans meeting as soon as they receive the list | questions: is MIG final? Comprehensive overview of process and data changes of NCTS 5 vs current NCTS, similar as the session for H7 | archive
MASP | specs and project | Question from WG how the different data sets for the MASP roll out will be distributed, checked, discussed. Is it an idea to start a subwork group that continuously deals with this? | 2021-01-28 |  |  |  | New |  |  | New |  | update? | BC: customs are open to this BE: is also high level in WG digital strategy BC: Here we would do separate sessions to look in detail at the messages & flows + test sessions action CRNSP -> list content + agenda | Agenda: dataset per dataset, calender is depending on Belgium MASP planning Inform about business process changes Review data requirements Review MIG documentation Review examples of messages Review test scenarios Follow up each subwerkgroep meeting | archive
eGlobalisation | antidumping | Customs mentioned during infossession that additional duties, such as antidumping would be accepted for eGlob. Question raised to dept legal internally in BE customs | 2021-03-10 | [8 empty] | new topic | BE: Consultation at the beginning of April within customs. A number of conditions have been drawn up-> are at customs for further analysis. The aim is to submit the definitive list of conditions to BC -> 2nd-3rd week of April, the aim is to provide feedback | Understanding is that this is included. Requirement is option in customs authorisation EIDR and AEO status. Propose to archive. | archive
eGlobalisation | omschrijving goederen | Welke omschrijving van goederen moet gebruikt worden | 2021-03-25 | [8 empty] | Informatief vanuit douane | BC: this must be as described in PLDA and in the legislation -> trade description This will also have to be the case in IDMS | Status update? | idem PLDA, archive, commercial description
eGlobalisation | insturen final - aantal subsequents | foutboodschap ontvangen rond aantal aanvaardde subsequents - hoe moet dit opgelost worden | 2021-03-25 |  |  |  | New | [5 empty] | BC: will write query so that PLDA helpdesk can handle this. Ideally, we get a list of sequence numbers received so that we can compare them with our own information | confirmation whether Helpdesk has received query and is informed that this can be asked by the operators. | archive
PLDA | Locatiecodes | Lijst is niet volledig/wordt niet aangeleverd | 2021-03-25 | [9 empty] | BC: will forward these, and set up an internal procedure so that they are forwarded monthly Martin: ask to forward payment methods & validation rules again | Status update? Can we receive the location codes and the overview of valid payment methods and validation rules? | archive
Emergency procedures | communication start/end emergency procedure | Regional forum Leuven: request was submitted to faster communicate end of emergency procedure, in particular in the weekends. Also the start timing of emergency procedure must be respected. Request to start emergency procedure at the communicated timing and immediately communicate the end of the emergency procedure when it is actually ended. | 2020-07-02 |  | Sophany |  | New topic | 2020-07-02 | Sophany/Bart will check internally with Helpdesk | status? |  |  | is included with helpdesk. Currently no more comments from the business to be archived | proposed improvement is to send an email notification in case the emergency procedure is closed. Remark: email lists to be checked? Alternatively: RSS feed | RSS feed for all updates, including end of emergency procedure
NCTS 5 | Specs not clear | Unclear reference to list of customs offices of departure in NCTS5 specs | 2020-07-02 |  |  |  | New topic | 2020-07-02 | to be checked | status? |  |  | JG: some code lists would be missing -> include in information session NCTS5 (lower) BC: Additional issues will be published. The functional specifications have yet to be finalized by Europe | Status update? | Specs OK, but national code list tables not yet available.
PLDA | Definition exporter | Definition Exporter: is there a validation rule? | 2019-11-28 |  | Bart Cieters |  | update? | 2020-07-02 | Info received but analysis has to be done. Part of PLDA20.2. Request was sent to 'dienst Wetgeving'. If a validation rule has to be introduced, then it will be implemented. | status? |  | update? | no progress |  | to be archived
NCTS 5 | NCTS + EIDR message | What is the status of this change request? Request was to stop with submitting excel spreadsheets to discharge NCTS when shipment is declared for entry in customs warehouse. |  |  | Bart Cieters |  | WIP. No update Update? | 2020-05-13 | No Update | status? | Voorlopig onhold |  | on hold |  | quid in new system? | status or to be archived? | Focus is on the MASP Projects | to be archived
PLDA | Charge report | Can it be confirmed that charge report does not to be sent anymore to BruCloud? | 2021-11-16 | Martin Goblet | [10 empty] | new | status? | Can be confirmed. | to be archived
EMCS | Certificates issue | Difficult to get certificates EMCS in particular. Several weeks. Currently manual system. Issues with mapping as well, no feedback. | 2019-11-20 |  | Sjoerd |  | Acceptable procedure should be that request for certificate is at the latest the week after installed. Sjoerd will check what went wrong and will provide feedback Ann has sent the samples, no update Update? | 2020-05-13 | No update available | status? |  | renewal of certificates is unclear and slow: what are the improvements? After 3 years, the certificates have to be renewed. This is resulting always in the need to use emergency procedure | BC: with EMCS this should be OK within 2 days. With PLDA -> 1 week. Martin -> certificate is retrieved from mail on request -> must be zipped, but also there problems -> mainly organizational problem because of mail traffic. Option to forward via FTP? Dorothy -> at each renewal form must be filled in -> labor intensive + send everything again action Customs > set up procedure for forwarding certificates by e-mail. | status action to develop procedure? | Remark: certificate renewal cannot be sent to customs helpdesk (spam). Should be via website to upload. Is insecure process. Question: will EMCS stay outside technical and authentication mechanism of IDMS/AES? | status? | No upgrade planned in the near future. Certificate : the public part of the certificate has to sent to the helpdesk. Before sending the extension has to be changed to .txt. | solution works apparently. Proposal to be archived.
eGlobalisation | average prices/customs valuation | Question about usage of average prices/customs valuation | 2021-03-10 | [8 empty] | new topic | action by Rudi Lodewijckx -> is operational issue. | Status update? | status? | status? | Indien de operator hiervoor een vergunning heeft, kan dit binnen e-globalisatie gebruikt worden. | to be archived
AES | specs | XSD is not complete. Missing: ctypes.xsd, doc.xsd, htypes.xsd, stypes.xsd en tcl.xsd. | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | Specs have been updated. | to be archived
AES | specs | Is it possible to combine 2 procedures (eg B1 export and B2 export for outward processing) in 1 declaration? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | This is allowed. Each article can have a distinct customs procedure. However, we would prefer that such complex declarations would be split up into multiple declarations. | Specs zijn volledig.
IDMS | specs | IE415 message contains a MRN. Is this correct and if so, when to be used? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | This correct. MRN will be added for lodging the supplementary declaration. | new
PLDA | code 3001 approved exporter | approved exporter seems to be required by local customs for import declarations | 2021-05-19 | Martin Goblet |  |  | New | [7 empty] | status? | to be archived? | In the new system it is clear that we have to avoid the use of national codes. CRSNP has made a document with an 'analysis' and in other MS they were able to skip most of the national cdes. The document will be shared. Examples have been shared for national produced document 3001, | document to be delivered | Topic is not for this workgroup Communication is delivered by Jim Styleman to Bart Engels for follow up (received) | archive
PLDA | Charge report | When airwaybill was used previously, and this airwaybill is reused later (because original AWB is deleted internally) and the AWB is not cancelled by the owner, then charge report is refused. Proposal is that helpdesk can do a reset in such exceptional cases | 2021-11-16 | Martin Goblet | [10 empty] | new | status? | AWB has to be unique in the current year. If it isn't properly cancelled , there is indeed an errormessage. The AWB has to be properly cancelled. A new case will be investigated | Martin has sent details to customs; was special case, no new issues for the moment | Special case, so no action because we want to limit the maintenance on the current application. Cause Transfer MIG not sent around - update PLDA 21.5? Is an error within customs. Include further in MoU meeting to include in validation process -> test together with SW providers | archive
TARBEL | Specs not clear | Meeting with European Dynamics on 28/5/2019, but the outstanding issues are still not resolved. Every last day of the month is missing. So TARIC upload is not usable. Specifications are also missing. Test environment not up to date. | 2020-09-16 | Ziegler | [5 empty] | status about documentation/specs? | ED has delivered a solution. Installation is ongoing. |  | EEG specs are needed but they are not public. BC examines with Sonja Dubois how these can still be distributed | Status update? | Specs still not available | status? | Specs have been sent to the softwarehouses. | Specs received, to be further checked | Martin indicates that these are correct, but has not had time to check them thoroughly - > can be archived | archive
eGlobalisation | print | print per email: vraag of print zou moeten werken. het werkt niet | 2022-03-09 | [14 empty] | new | Document via site is for financial settlement within FPS Fin itself - only calculated duties are correct - rest is incomplete. Customs will not provide a printout for operations - > Can be archived | archive
AES | specs | DAT inco term not allowed in PLDA, will it be enabled in AES/IDMS? | 2022-03-09 | [14 empty] | new | DAT inco term is allowed in PLDA and will be used in AES Dorothy Verthe: DAT would not work? Bart C - > declarations have been validated on this - Dorothy checks | archive
AES/IDSM/NCTS5 |  | Volgens de presentatie van het MASP moeten technische vragen gemaild worden naar “@sevicedesk”, wat is daar het e-mailadres voor? | 2022-03-09 | [14 empty] | new | Technical questions have to be send to the helpdesk | archive
eGlobalisation | helpdesk query details | query zou volgens Helpdesk niet bestaan om in testfaze controles te krijgen. Ifv verschillen die teruggekregen worden. Helpdesk weet niet af van script om query te draaien. Totaal bedragen en subsequentnr wel. | 2022-03-09 | [14 empty] | new | In progress. Helpdesk has received basic queries which can be extended. | helpdesk assistance for these queries is appreciated | closes | YES | archive
MASP | specs | Aangezien op de voordrachten van het nationaal forum verwezen werd naar de site van de EU voor meer informatie dacht ik daar de antwoorden op mijn vragen te vinden ivm AES en IDMS maar daar vind ik precies ook zeker niet alles of ik zoek op de verkeerde plaats. Is https://svn.taxud.gefeg.com/svn/Documentation/EUCDM/EN/index.htm de plaats waar ik informatie zou moeten vinden of is er een site voor ontwikkelaars met volledigere informatie? Volgens deze site komt er maar een update in Q3 van 2022. B.v. bij 12 04 000 000 Additional reference staat als ref ID5 “NEW”. Waar zijn de nieuwe beschikbaar? Indien ze er nog niet zijn wat is de planning en zullen er bestaande aangepast worden om de nieuwe als het ware tussen te voegen. | 2022-03-09 | [14 empty] | new | This link is a link to annex B. Annex B is the base for the technical specs of all the applications. |  | close | YES | archive
AES | period messages available | new system: quid annulment of exit confirmation, legally allowed 90 days, system requirement seems to be maximal 1 month (contradiction) | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | Under discussion | status? | The priority at the moment is to adjust the declaration-related functionalities. The export process will be maintained for the time being. As soon as we have a detailed analysis, we will be able to communicate a deadline. | status? | Export proces will remain the same for now, close | YES | archive
IDMS | specs | Guarantee: now the 49 account is declared. Does it have to be declared in the guarantee? Quid FRCT accounts? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | Under analysis | new | No update | status? | AAD&A/AGD&A : FRCT must be mentioned in deffered payment account, no longer in guarantee. Also the case in H7 | YES | archive
IDMS | specs | Currently a guarantee can be declared in case of IPR (code TVRY0, TVRY3 ea). Will it be maintained with the same codes? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | Under analysis | new | No update | status? | AAD&A/AGD&A :will be different codes, but functionality will remain | YES | archive
IDMS |  | klopt het dat hier geen zegels meer opgegeven kunnen worden? | 2022-03-09 | [14 empty] | new | Messages are based on CCI-meesage. In IE415 no seals are foreseen and in the current Import system you can't add seals either. | question closed | archive | YES | archive
AES/IDMS |  | E1/E2: T2L(F) valt onder UCC Proof of Union Status (PoUS) blijft dit momenteel ongewijzigd onder PLDA? Indien dit het geval is wanneer wordt hier een aanpassing van verwacht? | 2022-03-09 | [14 empty] | new | POUS is not part of these projects. As already explained in other meetings this is a seperate project. 1st phase foreseen in 2024 | To what system T2L(F)'s and AC4 have to be communicated? Or, alternatively, can the T2L(F) be created as a simple PDF? | AAD&A/AGD&A : T2LF remains in PLDA, as from 2024 - this will be in PoUS (EU system) , AC4 remains in PLDA close | YES | archive
AES |  | qualifierOfIdentification: volgens C0394 is bij qualifierOfIdentification = X een EORI verplicht en mag er geen adres opgegeven worden, maar in het bestandje “Location code identifiers AES” staat voor X “EORI + Address” welk is correct? | 2022-03-09 | [14 empty] | new | The possible ways of specifying a location code will initially be more limited than shown in the diagram. A transitional measure is being worked on, as many projects run in parallel. As soon as there is an unambiguous version, the table will be updated. | see above 'location codes' | see above 'location codes' - close | YES | archive
IDMS |  | XSD: Voor IE415 staat er “declarationAcceptanceDate”, in IE429 “dateOfAcceptance” volgens de MIG gaat het om inhoudelijk hetzelfde (15 09 001), klopt dit? | 2022-03-09 | [14 empty] | new | Is the same | status? | is the same, Close item | YES | archive
IDMS/AES/NCTS5 |  | plaats goederen: Waar kan er meer informatie verkregen worden over de precieze inhoudelijke betekenis van de codes/omschrijvingen voor types locaties (16 15 045 000). Onder wat valt b.v. een vergunning LLP? En presentatie bij het kantoor van vertrek? | 2022-03-09 | [14 empty] | new | The possible ways of specifying a location code will initially be quite limited. A transitional measure is being worked on, as many projects run in parallel. As soon as there is an unambiguous version, an overview of the possibilities will be given. | see above 'location codes' | see above items regarding location codes- close | YES | archive
AES |  | IE515: Als de EORI van de “Representative” overeen komt met deze van de “Declarant” mag deze niet opgegeven worden (R0893) maar deze tag is verplicht binnen de “Representative “. Hoe kan de status dan gedefinieerd worden in geval van vertegenwoordiging zonder subcontractant, i.e. exporteur (eigenaar van de goederen) geeft rechtstreeks opdracht aan de douaneagent/declarant? Of is de “representative” nu slecht van toepassing bij subcontractanten b.v. als de eigenaar van de goederen (de exporteur) aan de transportfirma opdracht geeft om ook de aangifte op te maken en deze transporteur deze laat opstellen door een douanedeclarant en in dit geval de exporteur de “exporter” is, de transporteur de “representative” en de douaneagent de “declarant”? | 2022-03-09 | [14 empty] | new | The possible ways of specifying a location code will initially be quite limited. A transitional measure is being worked on, as many projects run in parallel. As soon as there is an unambiguous version, an overview of the possibilities will be given. | please review this answer, it looks as if it is copied from the cell above. The answer is not for this question. | Wouter :In both examples, the customs agent is the representative. If the carrier has the declaration drawn up, he is the declarant and the exporter is the exporter. If the exporter has the declaration drawn up himself, he is the declarant and no separate exporter is mentioned. In both examples, the customs agent is the representative. If the carrier has the declaration drawn up, he is the declarant and the exporter is the exporter. If the exporter has the declaration drawn up himself, he is the declarant and no separate exporter is mentioned. close | YES | archive
AES |  | B1: Blijft in België een factuurnummer (N380/N328) verplicht bij een export (B1)? | 2022-03-09 | [14 empty] | new | No change is planned in this regard. | is our understanding correct that no invoice reference need to be mentioned for export according to the European specs? | Wouter : invoice number will remain mandatory, also in EU specs -< minimum 1 supporting document (=invoice) close | YES | archive
IDMS |  | DV1: Vervalt N934/C602 (DV1) of wordt dit terug een formulier? | 2022-03-09 | [14 empty] | new | Data-elements of DV1 are part of the dataset and already in the IE415 message | question closed | close | YES | archive
UCC |  | Jim Styleman - Vak 44 - BTW nummer geaddresseerde - blijft deze verplichting/mogelijkheid? | [16 empty] | Will be under fiscal references | question closed | close | YES | archive
monthly extracts | not received | we did not receive the monthly extracts | 2022-05-18 | [16 empty] | new | AAD&A/AGD&A : I will send them |  | archive
releases/maintenance | concern for impact on different systems seems not always clear | eg: H7 IDMS last week | 2022-05-18 | [16 empty] | new | Nick K : concern regarding high level view when systems go down and the impact on other systems. How is the impact analysis done? Internal ICT alignment was done to avoid this. H7 should not be updates togehter with Tarbel Next Sunday/Monday 5&6/6 - ICT maintenance - Weblogic and H7 together -> what will be the impact. AAD&A/AGD&A : Weblogic is only critical for older applications Nick : last time 10 days in emergency procedure AAD&A/AGD&A : we will do our best to avoid this | YES | archive
AES |  | IE515: klopt het dat hier geen taal meer opgegeven dient te worden? | 2022-03-09 | [14 empty] | new | The national data elements have to be added | What is the intention for this? CRNSP recommends not to add national data elements, or to keep it to an absolute minimum. | AAD&A/AGD&A : goal is to follow the EU specs as much as possible, AAD&A/AGD&A /Wouter : language will have to be mentioned (nat requirement) close | YES | language code in enveloppe, notin dataset; except for NCTS; archive
eGlobalisation | validation issue | For weekglobalisation, test system seems to validat only at end of month instead of week | 2021-03-10 | [8 empty] | new topic | Ticket is drawn up internally at customs. Especially fond is to avoid abuse | Status update? | status? | status? |  | new | No update | status? | The 10th day after the end of the month proves difficult in practice for the operators - customs will conduct an internal follow-up on the declaration and the validation rule has been set to 180 days. -> is already the case Weekglob validation has also been put on hold. Customs ask to cancel those declarations, but not if there is a PLDA declaration IM z -> they will be able to link that internally to the E-glob. Customs will contact customers with declarations that are still pending |  | when is new version in PLDA test? This version would contain also the IPR update? | No extra validation will be added. Topic can be archived | archive
eGlobalisation | validation date | only validation of the month, not year; PLDA accepts date with other year | 2022-03-09 | [14 empty] | new | MSPPLDA-29469 has been created. Part of PLDA 22.1 | when 22.1 | 22.1 is scheduled for August |  | status? To be tested? | No extra validation will be added. Topic can be archived | archive
eGlobalisation | globalisation for entry under 51 procedure (IP) | When will eGlob be available for customs procedure 51 (entry under IP)? | 2022-05-18 | [14 empty] | new |  | status? | Version 22.1 - August |  | status? To be tested? Is testing period foreseen? | Is part of PLDA 22.0.2. Version has been delivered. | archive
NCTS 5 | code lists | code list for Ukrain customs offices not yet available | [20 empty] | new | This should be available on: https://taxation-customs.ec.europa.eu/online-services_en | archive
EMCS 4.0 | testing | when is the test environment available + new ARC structure as of February -> will this also be testable? | [20 empty] | new | De EMCS Phase 4.0 testomgeving zal beschikbaar worden gesteld in de loop van oktober 2022 zoals eerder aangekondigd. De exacte url van de webapplicatie en de endpoint wordt gepubliceerd op de Internetpagina's van de AAD&A. Wat betreft de "wijziging" in de ARC is er geen enkele impact aangezien die door de AAD&A wordt gegenereerd. Het formaat blijft identiek en er is enkel een indicatie die aanduidt of het een e-AD dan wel een e-SAD betreft. Die informatie zit uiteraard ook in de IE815/801 (Message Type). Voor meer informatie omtrent de wijzigingen, zie ook de presentatie en specificaties op https://financien.belgium.be/nl/douane_accijnzen/ondernemingen/applicaties-da/technische-documentatie-0/emcs#q4. Aangaande testing van EMCS Phase 4.0 kan er rechtstreeks via mail contact genomen worden met de tweedelijnssupport (emcs.support@minfin.fed.be); enkel en uitsluitend in het kader hiervan (bijvoorbeeld aanmaken testvergunning, bevestiging van betaling accijns ter validatie van het bericht van ontvangst). Op de vraag of de economische operator moet beschikken over een 'nieuwe' SEED-vergunning (van het type (tijdelijk) gecertificeerde afzender, (tijdelijk) gecertificeerde geadresseerde)) om met e-SAD te kunnen werken, is bevestigend geantwoord. | archive
IDMS | specs | Guarantee: Is it possible to declare more then 1 guarantee in 1 declaration? | 2021-11-16 | Johan Geerts | [10 empty] | new | status? | According the specs it is possible, but we will allow only 1 customer account. | new | No update | status? | AAD&A/AGD&A : will most likely be 1, but to be confirmed |  | status? | Only 1 | archive
NCTS 5 |  | Tabel CL716 ControlType vinden we niet (ook niet via https://ec.europa.eu/taxation_customs/dds2/rd/rd_download_home.jsp?Lang=nl) | 2022-03-09 | [14 empty] | new | According COM this is a confidential CL. Will investigate with BA. | status? | AAD&A/AGD&A : EU declines request to publish codelist. Johan Geerts -> in NL this list is available close | NO | is published in NL! | As already specified, CL716 is a confidential CL and can't be shared. | archive
AES |  | Update MIG | [18 empty] | Wouter : new MIG is available, but communication end-point is not available yet MIG will be published ASAP. -> addition language codes+ supplementary codes no additional meeting seems necessary -> members to check when specs are available | NO | status? | MIG was published | archive
PN,TS | process | is PN required for EU status goods? Assumption was that EU goods would be cleared in ICS2 | [20 empty] | new | A PN (IETS007) is required for Union goods (no TSD). Each consignment will need to refer to at least 1 previous document of type = proof. IETS007 message specs (BR and CL) have been changed for this, also part of new version of the MIG | we suggest that this answer should be published in Q&A on the website | Will be added to FAQ Archive?
PN | validation rule | for EU goods, will the availability of T2L document be checked? | [20 empty] | new | Not automatically, but reference is needed in previous document section, if not IETS007 will be rejected The PN will (after GO LIVE of PoUS) send the MRN to PoUS that will check the T2L/T2LF in the CR and send back a validation to the PN system | we suggest that this answer should be published in Q&A on the website | Will be added to FAQ. Archive?
TS | process | must goods that arrive with NCTS be declared with TS if there is no intention to place under TS? | [20 empty] | new | No, until NCTS P5 clear-off remains within NCTS, so no TSD is needed. As from NCTS P5, a TSD will be needed after T1 transit, but the PN-TS system will probably automatically register transit declaration data as TSD, so that no new submission is needed. This mechanism is to be elaborated in the next phase of PN-TS. | we suggest that this answer should be published in Q&A on the website | Will be added to FAQ. Archive?
TS | message | FR MIG contains message for controls: IETS460 (control) IETS18 (results of control: is this also foreseen in BE MIG? | [20 empty] | new | In de nieuwe versie van de BE MIG, is inderdaad IETS460 opgenomen. Er bestaat geen IETS18 bericht en het control result zelf wordt niet gecommuniceerd aan de EO, enkel een TSD status update notification IETS095, wat wel het control result weerspiegelt (bvb. bij conform: status update van 'UNDER CONTROL' naar 'ACCEPTED'). Dat bericht is ook opgenomen in de nieuwe versie van de MIG. | we suggest that this answer should be published in Q&A on the website | Will be added to FAQ. Archive?
MASP | email adress for questions | email adress for questions regarding the new systems will be delivered | 2022-03-09 | [12 empty] | new |  | when? | Technical questions to the helpdesk Functional questions to economic support FAQ to be published on website of Customs Administration | status FAQ? This to avoid waiting for answers to questions that earlier were asked. | FAQ has been published but not yet for IDMS |  | status? | Technical questions can be sent to the PLDA Helpdesk. | OK, but no answers and no answers on Q&A

## Meeting dates
WG R&D | 2020-01-23
CRSNP | 2020-03-11
WG R&D | 2020-03-26 | Koen Meyskens will take over
CRSNP | 2020-05-13
WG R&D | 2020-05-28 | vraag om digitaal te doen
WG R&D | 2020-07-02
WG R&D | 2020-09-24
WG R&D | 2021-03-25
WG R&D | 2021-06-03
CRSNP | 2022-11-10
WG R&D | 2022-11-24
WG R&D | 2023-01-26