## Followup
Topic | Issue | Description | Issue date | CRNSP owner | Owner | Due date | Status | Status date | comment customs | Status CRNSP 20/1/2021 | Meeting WG R&D 28/1/2021 | Status CRNSP 10/3/2021 | Meeting WG R&D 25/03/2021 | Status CRNSP 19/5/2021 | Status CRNSP 16/11/2021 | Meeting WG R&D 16/12/2021
General | SLA/MoU | Proposed SLA/MoU will be discussed internally and the remarks will be shares asap | 2019-09-26 |  | Chris Declerck | not known | Markup MoU/SLA received and under review for reaction | 2020-05-13 | Markup MoU/SLA submitted to stakeholders and topic to be discussed in Steering Group | Any update? |  | update? | Bart E: no update yet, Pieter would contact Johan VD -> has this already taken place? This must be done first. Customs is waiting for input from Johan action : Pieter Haesaert | According to Johan Van Dingenen, there was no contact yet with Chris on this point. | Johan Van Dingenen is consolidating remarks. Steering committee requested MoU progress. Status? | First draft version has been made after several meetings between Johan Van Dingenen and Chris Declerck
PLDA | Definition exporter | Definition Exporter: is there a validation rule? | 2019-11-28 |  | Bart Cieters |  | update? | 2020-07-02 | Info received but analysis has to be done. Part of PLDA20.2. Request was sent to 'dienst Wetgeving'. If a validation rule has to be introduced, then it will be implemented. | status? |  | update? | no progress |  | nieuw systeem | No update
PLDA |  | Intracom Meerdere klanten maken melding van onderstaande fout die ze krijgen in PLDA Error NO VALID VAT NR Dit in het geval er een BTW nr gebruikt wordt, waarbij de landcode niet overeenstemt met de prefix Als een Nederlander gebruikt maakt van een Duits BTW nr, krijg je problemen. Het land stemt dan niet overeen met de prefix van de geadresseerde, en daar krijgen klanten nu een fout op. |  |  | Bart Cieters | PLDA 21.1 | New topic |  | Ticket created Part of PLDA20.2 | status? Each time this issue occurs, country code has to be changed and has to be equal to the country code of the VAT nr? | PLDA20.6 |  | will be in PLDA21.1. 20.6 no longer exists. 21.0 -> already first changes for IDMS (connection with PLDA) + single window | adapt the country code + in Algen code real code to be mentioned? This is an old bug. Is this the correct procedure? Will it be in production 1 Jan 2021? | status? | Solved
PLDA | code Y040 | code Y040: export moet je altijd een BTW nummer toevoegen. In sommige gevallen is geeen Y040 nodig, bvb indien het een buitenlandse BTW plichtige is. Helpdesk stelt voor om het BTW nummer van de douane-expediteur te melden (wat uiteraard wettelijk niet juist is). Dit geval komt met name voor bij regeling 3171 (wederuitvoer uit douane-entrepot). | 2020-09-16 | Ziegler | [5 empty] | status? | Still to be done |  | Still to be done | Status update? | remark for new AES?
PLDA | code 3001 approved exporter | approved exporter seems to be required by local customs for import declarations | 2021-05-19 | Martin Goblet |  |  | New | [7 empty] | status?
PLDA | Charge report | When airwaybill was used previously, and this airwaybill is reused later (because original AWB is deleted internally) and the AWB is not cancelled by the owner, then charge report is refused. Proposal is that helpdesk can do a reset in such exceptional cases | 2021-11-16 | Martin Goblet | [10 empty] | new
PLDA | Charge report | Can it be confirmed that charge report does not to be sent anymore to BruCloud? | 2021-11-16 | Martin Goblet | [10 empty] | new
EMCS | Certificates issue | Difficult to get certificates EMCS in particular. Several weeks. Currently manual system. Issues with mapping as well, no feedback. | 2019-11-20 |  | Sjoerd |  | Acceptable procedure should be that request for certificate is at the latest the week after installed. Sjoerd will check what went wrong and will provide feedback Ann has sent the samples, no update Update? | 2020-05-13 | No update available | status? |  | renewal of certificates is unclear and slow: what are the improvements? After 3 years, the certificates have to be renewed. This is resulting always in the need to use emergency procedure | BC: with EMCS this should be OK within 2 days. With PLDA -> 1 week. Martin -> certificate is retrieved from mail on request -> must be zipped, but also there problems -> mainly organizational problem because of mail traffic. Option to forward via FTP? Dorothy -> at each renewal form must be filled in -> labor intensive + send everything again action Customs > set up procedure for forwarding certificates by e-mail. | status action to develop procedure? | Remark: certificate renewal cannot be sent to customs helpdesk (spam). Should be via website to upload. Is insecure process. Question: will EMCS stay outside technical and authentication mechanism of IDMS/AES?
EMCS | Feb 2022 2-yearly upgrade | In Feb 2022 we can expect the 2 yearly update of EMCS. Normally, Jurgen gives us an overview of the changes. When can we have this overview? | 2021-05-19 |  |  |  | New | [7 empty] | details to be received
TARBEL | Specs not clear | Meeting met European Dynamics op 28/5/2019, maar de openstaande punten zijn nog altijd niet opgelost. Elke laatste dag van de maand ontbreekt. Dus TARIC upload is niet bruikbaar. Specificaties ontbreken ook. Testomgeving niet up to date. | 2020-09-16 | Ziegler | [5 empty] | status about documentation/specs? | ED has delivered a solution. Installation is ongoing. |  | EEG specs are needed but they are not public. BC examines with Sonja Dubois how these can still be distributed | Status update? | Specs still not available
eGlobalisation | specifications | Rudi Lodewijckx will check whether eGlobalisation is also intended for customs procedure 5171, or if this procedure can be allowed with only EIDR in case it is the same autorisation holder | 2021-01-28 |  | Rudi Lodewijckx |  | New |  |  | New |  | update? | BC: consulted with Rudi. BC will come back to this. | Status update? | status? | À partir du 1er février 2022, l'utilisation de l'e-globalisation sera obligatoire. Toutefois, un report est encore possible pour les régimes énumérés ci-dessous : Régime 51 (Perfectionnement Actif) : le report de la globalisation hebdomadaire et/ou mensuelle est possible jusqu'au 31 décembre 2022. Régime 6121 (Perfectionnement Passif) : le report de la globalisation hebdomadaire et/ou mensuelle est possible jusqu'au 31 décembre 2022. Dans les deux régimes, la méthode de travail actuelle peut être maintenue jusqu'à la fin de la période de report. Les opérateurs qui sont prêts avant cette échéance peuvent, bien entendu, intégrer les dispositions ci-dessus. Les tests sont possibles. Régime 4400 (Destination Particulière) : pas repris pour le moment. Les informations sur la date de mise en œuvre suivront après l’implémentation de l'IDMS - ALL. Cela signifie que les tests ne sont pas possibles pour le moment. Pour le régime susmentionné, la pratique actuelle sera maintenue jusqu'à nouvel ordre.
eGlobalisation | validation issue | for weekglobalisation, test system seems to validat only at end of month instead of week | 2021-03-10 | [8 empty] | new topic | Ticket is drawn up internally at customs. Especially fond is to avoid abuse | Status update? | status? | To be solved
eGlobalisation | average prices/customs valuation | Question about usage of average prices/customs valuation | 2021-03-10 | [8 empty] | new topic | action by Rudi Lodewijckx -> is operational issue. | Status update? | status?
MASP | planning | Is planning outlined feasible? | 2021-11-16 | [11 empty] | new | No update about the planning
MASP | subwork group/workshop | Can a subworkgroup be established for evaluation of MIG's? | 2021-11-16 | [11 empty] | new | Yes
MASP | planning | documentation, MIG's should be complete and finalized 8 months before go live date | 2021-11-16 | [11 empty] | new | deadline for the migs will be taken up in MOU.
MASP | instructions | Are there transition measures? Will the administrative instructions be kept up-to-date? What about amend, annull, regularisations of declarations? | 2021-11-16 | [11 empty] | new | Analysis ongoing
NCTS 5 | Pull mechanism | No reference to URL of oneGateway for PULL mechanism. Does this mean that the PULL mechanism cannot be used for NCTS? | 2021-11-16 | Johan Geerts | [10 empty] | new | Pull will be foreseen
NCTS 5 | National code lists missing | National code lists are not yet published | 2021-11-16 | Johan Geerts | [10 empty] | new | National codelists will be drafted as soon we receive the necessary info from the legal department
NCTS 5 | NCTS + EIDR message | What is the status of this change request? Request was to stop with submitting excel spreadsheets to discharge NCTS when shipment is declared for entry in customs warehouse. |  |  | Bart Cieters |  | WIP. No update Update? | 2020-05-13 | No Update | status? | Voorlopig onhold |  | on hold |  | quid in new system? | No update
AES | specs | XSD is not complete. Missing: ctypes.xsd, doc.xsd, htypes.xsd, stypes.xsd en tcl.xsd. | 2021-11-16 | Johan Geerts | [10 empty] | new | Published
AES | period messages available | new system: quid annulment of exit confirmation, legally allowed 90 days, system requirement seems to be maximal 1 month (contradiction) | 2021-11-16 | Johan Geerts | [10 empty] | new | Under investigation
AES | specs | Is it possible to combine 2 procedures (eg B1 export and B2 export for outward processing) in 1 declaration? | 2021-11-16 | Johan Geerts | [10 empty] | new | Under investigation
AES | specs | Supplentary declarations X or Y: are these 2 new declarations following the initial declarations and, as a consequence, with a separate LRN and MRN, or can the same LRN be used as in the initial declarations? | 2021-11-16 | Johan Geerts | [10 empty] | new | The complementary declaration uses the same LRN as the initial declaration. Otherwise, we will not be able to identify the original declaration. The original declaration will be updated, so no new MRN is created.
AES | specs | Location codes: in case of centralized clearance with export from NL, is it possible to declare a NL location? If yes, how? Please provide a comprehensive explanation about the location codes to be declared as documented for NCTS in the excels. | 2021-11-16 | Johan Geerts | [10 empty] | new | There is no consensus so far about how reference data like location codes will be validated. The current plan assumes that there will be a list of all relevant location codes that we will check. However, we don't know yet what that table will allow us to verify. If that table doesn't materialize, we will be unable to determine which location codes or location identifier types are valid for each member state. In that worst case scenario, we would not verify the location code for centralized clearance, accept the declaration, and if we subsequently get an error message from the office of presentation, forward that to the declarant. When the declarant sends in an amendment of the declaration, the message will be resent to the office of presentation.For Belgian location codes, you can find extra info on : https://financien.belgium.be/sites/default/files/Helpdesk_PLDA/MIG-Tech/AES/Location%20code%20identifiers%20AES.xlsx
AES | Definition exporter | Definition Exporter: is there a validation rule? | 2021-11-16 | Johan Geerts | [10 empty] | new | No validation foreseen
IDMS | specs | IE415 message contains a MRN. Is this correct and if so, when to be used? | 2021-11-16 | Johan Geerts | [10 empty] | new
IDMS | specs | Supplementary declarations X or Y: 2 separate new declarations? | 2021-11-16 | Johan Geerts | [10 empty] | new | The complementary declaration uses the same LRN as the initial declaration. Otherwise, we will not be able to identify the original declaration. The original declaration will be updated, so no new MRN is created.
IDMS | specs | Location codes: will the current list be maintained? What with centralized clearance with which goods can be imported via other country. Can the location codes of that other country be used? If so, how? | 2021-11-16 | Johan Geerts | [10 empty] | new | No
IDMS | specs | Special procedures: there are many new data elements. Explanation needed how these have to be used. Does it impact on the existing reporting? Are the current lists of IPR maintained? | 2021-11-16 | Johan Geerts | [10 empty] | new | Under investigation
IDMS | specs | Guarantee: now the 49 account is declared. Does it have to be declared in the guarantee? Quid FRCT accounts? | 2021-11-16 | Johan Geerts | [10 empty] | new | Under investigation
IDMS | specs | Currently a guarantee can be declared in case of IPR (code TVRY0, TVRY3 ea). Will it be maintained with the same codes? | 2021-11-16 | Johan Geerts | [10 empty] | new | Under investigation
IDMS | specs | Guarantee: Is it possible to declare more then 1 guarantee in 1 declaration? | 2021-11-16 | Johan Geerts | [10 empty] | new | Under investigation